## Master_Checklist
Workstream | Task | Tier | Mandatory for | Owner | Status | Evidence link / note | Blocker if missing?
Product | Locale selected and mapped in locale matrix | All | All locales | PM | Not Started |  | Yes
Localization | Glossary approved | Tier 1-2 | Customer-facing locales | Localization Lead | Not Started |  | Yes
Localization | Tone guide approved | Tier 1-2 | Customer-facing locales | Localization Lead | Not Started |  | Yes
Localization | Screens translated in context | All | All locales | Translator | Not Started |  | Yes
QA | Screenshot review completed | All | All locales | LQA Reviewer | Not Started |  | Yes
QA | RTL layout checked | RTL | RTL locales only | LQA Reviewer | Not Started |  | Yes
QA | Text expansion checked | All | German/French/Russian etc. | LQA Reviewer | Not Started |  | No
QA | Input validation messages reviewed | All | All locales | LQA Reviewer | Not Started |  | Yes
QA | Body / posture wording reviewed for sensitivity | All | All locales | Native Reviewer | Not Started |  | Yes
Engineering | Auto locale routing tested | All | All locales | Engineer | Not Started |  | Yes
Engineering | Fallback language tested | All | All locales | Engineer | Not Started |  | Yes
Engineering | Number/date/unit formatting tested | All | All locales | Engineer | Not Started |  | Yes
Support | Macro replies localized | Tier 1-2 | Support locales | Support Lead | Not Started |  | No
Legal | Privacy / consent wording reviewed | Tier 1-2 | Markets with legal review | Legal | Not Started |  | Yes
Go-live | Native sign-off received | Tier 1-2 | Customer-facing locales | Locale Owner | Not Started |  | Yes
Go-live | Pilot rollout decision recorded | Tier 1 | Wave 1 locales | PM | Not Started |  | Yes

## Locale_Signoff
Locale | Wave | Locale Owner | Translator | Native Reviewer | Engineering QA | Product Sign-off | Legal Sign-off | Go-live Status | Comments
pl-PL | Wave 1 | [6 empty] | Not Started
en-US | Wave 1 | [6 empty] | Not Started
en-GB | Wave 1 | [6 empty] | Not Started
es-ES | Wave 1 | [6 empty] | Not Started
es-419 | Wave 1 | [6 empty] | Not Started
it-IT | Wave 1 | [6 empty] | Not Started
fr-FR | Wave 1 | [6 empty] | Not Started
fr-CA | Wave 2 | [6 empty] | Not Started
de-DE | Wave 1 | [6 empty] | Not Started
de-AT | Wave 2 | [6 empty] | Not Started
de-CH | Wave 2 | [6 empty] | Not Started
ar-SA | Wave 1 | [6 empty] | Not Started
ja-JP | Wave 1 | [6 empty] | Not Started
zh-Hans-CN | Wave 1 | [6 empty] | Not Started
zh-Hant-TW | Wave 2 | [6 empty] | Not Started
nl-NL | Wave 2 | [6 empty] | Not Started
sv-SE | Wave 2 | [6 empty] | Not Started
cs-CZ | Wave 2 | [6 empty] | Not Started
pt-BR | Wave 1 | [6 empty] | Not Started
pt-PT | Wave 2 | [6 empty] | Not Started
ru-RU | Wave 2 | [6 empty] | Not Started
hi-IN | Wave 1 | [6 empty] | Not Started
bn-BD | Wave 2 | [6 empty] | Not Started
ur-PK | Wave 2 | [6 empty] | Not Started
ko-KR | Wave 1 | [6 empty] | Not Started
tr-TR | Wave 2 | [6 empty] | Not Started
vi-VN | Wave 2 | [6 empty] | Not Started
fa-IR | Wave 2 | [6 empty] | Not Started
id-ID | Wave 1 | [6 empty] | Not Started
fil-PH | Wave 2 | [6 empty] | Not Started
mr-IN | Wave 2 | [6 empty] | Not Started
te-IN | Wave 2 | [6 empty] | Not Started

## Bug_Log_Template
Locale | Screen | String / component | Issue type | Severity | Screenshot link | Owner | Target fix date | Status | Retest result
de-DE | Photo capture | Button overflow in retry message | UI overflow | Major |  |  |  | Open
ar-SA | Results | RTL icon order reversed | RTL layout | Critical |  |  |  | Open

## Owners_Status
Role | Default owner | Definition of done
PM | Product owner | Wave, scope and release decision recorded
Localization Lead | Localization manager | Glossary, style guide and locale routing approved
Translator | Native translator | Strings translated in context
Native Reviewer | In-country reviewer | Grammar, tone and cultural fit approved
Engineer | Frontend / app engineer | Locale routing and fallback work
LQA Reviewer | Localization QA | Screenshot and functional LQA complete